## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | Set up multi-agent workflow foundation | Must Have | Existing project structure | Navya | Completed
Sprint 1 | Sprint 1 | US-02 | Implement Planning, Research, Analysis, Validation and Decision agents | Must Have | US-01 | Navya | Completed
Sprint 1 | Sprint 1 | US-03 | Integrate workflow execution with FastAPI /ask API | Must Have | US-01, US-02 | Navya | Completed
Sprint 1 | Sprint 1 | US-04 | Integrate PostgreSQL workflow and agent activity logging | Must Have | US-03 | Navya | Completed
Sprint 1 | Sprint 1 | US-05 | Build enterprise workflow frontend and monitoring pages | Must Have | US-03, US-04 | Navya | Completed
Sprint 1 | Sprint 1 | US-06 | Test workflow, dashboard and agent activity pages | Must Have | US-04, US-05 | Navya | Completed
Sprint 1 | Sprint 1 | US-07 | Push completed project changes to GitHub repository | Must Have | US-06 | Navya | Completed
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
SPRINT 1 BACKLOG
US-01 | T-01 | Review existing project structure | Project setup | Completed | 2 |  | Completed | 2
US-02 | T-02 | Implement and verify multi-agent workflow | Development | Completed | 6 |  | Completed | 6
US-03 | T-03 | Update FastAPI /ask endpoint and frontend integration | Development | Completed | 4 |  | Completed | 4
US-04 | T-04 | Implement workflow and agent activity database logging | Development | Completed | 4 |  | Completed | 4
US-05 | T-05 | Build frontend pages for dashboard, monitoring, workflows and agent activity | Development | Completed | 6 |  | Completed | 6
US-06 | T-06 | Execute API, frontend and database tests | Testing | Completed | 4 |  | Completed | 4
US-07 | T-07 | Commit and push final changes to GitHub | Deployment | Completed | 1 |  | Completed | 1
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | Project structure and module alignment needed. | Reviewed repository structure and identified required workflow components.
Sprint 1 | Day 2 | Agent workflow integration required verification. | Tested Planning, Research, Analysis, Validation and Decision flow.
Sprint 1 | Day 3 | API response needed alignment with workflow result structure. | Updated /ask endpoint to return final_decision correctly.
Sprint 1 | Day 4 | Database logging and dashboard data needed validation. | Verified workflow and agent activity records through PostgreSQL.
Sprint 1 | Day 5 | Frontend pages required end-to-end testing. | Tested home page, monitoring, workflows and agent activity pages.
Sprint 1 | Day 6 | GitHub branch/PR conflict required care. | Kept completed branch changes separate and avoided unsafe merge into team main.
Sprint 1 | Day 7 | Final repository update needed. | Committed and pushed final changes to Navya-Infosys and personal repository.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | Not recorded | Not recorded | Navya | Break work into smaller modules and test each change. | Avoid making large unverified merges during final integration. | Continue using Git branches and incremental commits. | Use smaller commits and verify before push.
2 | Sprint 1 | Not recorded | Not recorded | Navya | Test API and database changes together. | Avoid pushing unrelated/old dashboard files. | Keep secrets out of Git and use .env/.gitignore. | Reviewed files before staging and pushed only required project files.
3 | Sprint 1 | Not recorded | Not recorded | Navya | Document completed features clearly. | Delay final testing until the end. | Use frontend and backend checks after each feature. | Validated workflow, dashboard and monitoring functionality.
4
5
6
7